## Sheet1
ID | Assumption Description | Category | Date Logged | Owner | Impact if False | Likelihood of Failure | Source / Rationale | Validation Plan | Status | Review Date | Linked Items
A001 | The Buyer will provide timely access to relevant stakeholders for co-design sessions and feedback. | Stakeholder Access | 2025-06-12 | Bid Manager | Delay in system design and requirement clarification. | Medium | Based on need for collaborative development | Confirm availability in kickoff meeting. | Open | 2025-06-30 | Milestone 1
A002 | The Buyer has a stable and mature cybersecurity infrastructure compliant with Nova Britannia's standards. | Technical / Security | 2025-06-12 | Security Lead | Integration delays or redesign if security compatibility is lacking. | Low | Assumed from SOR security clause | Security assessment during Month 1. | Open | 2025-07-10 | Security Requirements
A003 | IoT data feeds and existing project software APIs are accessible and documented. | Technical / Integration | 2025-06-12 | Systems Architect | Real-time integration may be delayed or partial. | Medium | Live Data Integration Framework required per SOR | Interface test in prototype phase. | Open | 2025-08-01 | Milestone 2
A004 | Remote access infrastructure for multi-user collaboration already exists in Buyer’s environment. | Infrastructure | 2025-06-12 | Infrastructure Lead | Increases scope and cost if new setup required. | Medium | Implied in requirement for remote access | Infrastructure audit early in Phase 1. | Open | 2025-07-05 | Collaboration Suite
A005 | End users are familiar with basic digital tools and can be trained to use holographic interfaces with minimal effort. | User Capability | 2025-06-12 | Training Lead | Risk of poor adoption and high support demand. | High | SOR mentions minimal training required | Conduct user capability survey during pilot. | Open | 2025-08-15 | User Training
A006 | There will be no significant changes to scope during the first 9 months (before full deployment). | Scope Stability | 2025-06-12 | Project Manager | May require redesign and additional cost/time. | Medium | Needed to meet aggressive delivery schedule. | Confirm in contract negotiation. | Open | 2025-07-01 | Contract Management
A007 | The Buyer will approve invoices within 15 working days of submission, assuming documentation is complete. | Commercial | 2025-06-12 | Commercial Lead | May impact cash flow and resource planning. | Low | Based on clause in Payment & Invoicing section | Confirm in contract terms. | Open | 2025-07-01 | Payment Schedule
A008 | The project site in Aurelia will be accessible to our implementation team during deployment. | Logistics | 2025-06-12 | Delivery Manager | May delay onsite setup or require alternate plans. | Low | Deployment location specified in SOR | Verify access conditions during pre-deployment. | Open | 2025-09-01 | Deployment Plan
A009 | Cloud infrastructure required for the HPO will be available and approved by the Buyer. | Infrastructure | 2025-06-12 | Cloud Architect | Project delays due to cloud hosting or compliance approvals. | Medium | HPO requires scalable and secure cloud deployment. | Confirm infrastructure strategy during architecture phase. | Open | 2025-07-05 | System Architecture
A010 | Local regulations will permit remote access and cloud data storage for project information. | Compliance | 2025-06-12 | Compliance Officer | May require redesign for on-premise hosting. | Low | Remote access is listed as a requirement. | Review data residency laws and obtain written clearance. | Open | 2025-07-10 | Security Requirements
A011 | Funding will be available on time per the milestone schedule. | Commercial | 2025-06-12 | Finance Lead | Disruption in project cash flow and resourcing. | Low | Based on 10-year funding settlement. | Discuss funding flow and milestones in kickoff. | Open | 2025-07-01 | Payment Schedule
A012 | The Buyer's procurement and onboarding processes will not exceed 4 weeks. | Commercial | 2025-06-12 | Procurement Lead | Delays in start and delivery of Phase 1. | Medium | Based on typical government process. | Clarify timelines in pre-contract discussions. | Open | 2025-06-25 | Milestone 1
A013 | AI algorithms will have access to enough historical project data for initial model training. | Technical | 2025-06-12 | AI Team Lead | Degraded prediction accuracy in early stages. | Medium | AI system depends on historical data. | Request datasets during setup. | Open | 2025-07-15 | AI Decision Engine
A014 | User licenses for project management software (e.g., Primavera, MS Project) will be available to support integration. | Licensing | 2025-06-12 | IT Lead | May impact data access and integration. | Low | Required for live integration framework. | Confirm licensing during onboarding. | Open | 2025-06-30 | Data Integration
A015 | No third-party legal disputes or embargoes will interfere with system components or delivery. | Legal | 2025-06-12 | Legal Counsel | Could halt progress or require replacements. | Low | No indication of legal restrictions. | Check export/import compliance. | Open | 2025-07-10 | Hardware Delivery
A016 | Government change or reorganization will not alter project priorities within the first year. | Political | 2025-06-12 | Program Manager | Risk of cancellation or re-scoping. | Medium | Large national projects often span administrations. | Monitor policy and maintain communication with Buyer. | Open | 2025-09-01 | Project Charter
A017 | User feedback will be available within 5 working days of each test release. | Stakeholder | 2025-06-12 | UX Lead | Delays in iteration and improvement. | Medium | Feedback required per reporting structure. | Agree feedback SLAs with Buyer. | Open | 2025-08-01 | Beta Testing
A018 | The Buyer will support internal promotion and change management to encourage adoption. | Organizational | 2025-06-12 | Adoption Manager | Risk of resistance and low adoption. | Medium | HPO requires cultural buy-in. | Discuss change strategy at program kickoff. | Open | 2025-07-15 | Training Plan
A019 | Key technical resources assigned to the HPO project will not be reassigned to other projects for the duration of the contract. | Resourcing | 2025-06-12 | Delivery Director | Loss of continuity and technical knowledge, project delays. | Medium | Internal resource planning commitment. | Resource lock-in confirmed by PMO. | Open | 2025-07-01 | Resource Plan
A020 | Reusable components or legacy code used will not introduce unmanageable technical debt or security vulnerabilities. | Technical Quality | 2025-06-12 | Tech Lead | Potential security or maintenance issues in production. | Low | Code reviewed under internal reuse policy. | Conduct internal code audits prior to reuse. | Open | 2025-07-10 | Codebase Review
A021 | The internal development environment will remain stable and aligned with project tooling requirements. | Infrastructure | 2025-06-12 | DevOps Lead | Environment mismatches may delay builds or testing. | Low | Dedicated environment provisioned. | Environment checks at each release milestone. | Open | 2025-07-05 | CI/CD Pipeline
A022 | All subcontractors and third-party vendors will deliver on time and comply with the main contract’s requirements. | Third Party | 2025-06-12 | Commercial Manager | Could cause schedule slippage or quality issues. | Medium | Current vendor performance history. | Monthly vendor performance review. | Open | 2025-07-10 | Vendor Contracts
A023 | Internal approvals and governance (e.g., technical design boards) will occur within the planned timeframes. | Governance | 2025-06-12 | Project Manager | Delay in progressing key technical decisions. | Low | Internal governance timelines established. | Track governance schedules in PM tool. | Open | 2025-07-01 | Internal PM Plan
A024 | Internal security reviews and penetration testing will be scheduled without delay before deployment milestones. | Security | 2025-06-12 | Security Lead | Could delay system go-live or certification. | Low | Security resources provisioned internally. | Confirm slot in quarterly test schedule. | Open | 2025-08-01 | Security Testing Plan
A025 | Key delivery staff will remain under current contract terms without notice of departure for the next 6 months. | Resourcing | 2025-06-12 | HR Manager | Loss of critical expertise and handover delays. | Medium | Current contract stability and retention risk review. | Monitor HR risk register. | Open | 2025-07-15 | Resource Risk Register
A026 | Internal project management tools (e.g., Jira, Confluence) will be maintained with no outages affecting HPO tracking. | Tooling | 2025-06-12 | Tooling Manager | Could impact team coordination and reporting. | Low | High SLA from tool provider. | Tool availability reports. | Open | 2025-06-30 | Reporting Cadence
A027 | No reorganization or merger activity within the contracting organization will disrupt delivery capacity or resource focus. | Organizational | 2025-06-12 | Executive Sponsor | Strategic misalignment or loss of focus. | Low | No current M&A plans. | Quarterly business review check-ins. | Open | 2025-09-01 | Governance Meeting
A028 | Internal budget allocated for the project is sufficient and will not be reallocated to higher-priority initiatives. | Finance | 2025-06-12 | Finance Director | Budget shortfall may impact delivery quality or scope. | Medium | Annual financial plan approved. | Budget tracking and monthly variance reports. | Open | 2025-07-15 | Internal Budget Review
A029 | The Large Language Model (LLM) selected for AI decision support will maintain its API and feature stability over the project timeline. | Technology | 2025-06-12 | AI Systems Architect | Integration issues or rework if API changes unexpectedly. | Medium | LLM vendor has a strong roadmap and stable release history. | Monitor vendor release notes and deprecation notices. | Open | 2025-08-01 | AI Decision Engine
A030 | The underlying AI model used will remain licensed and commercially available under current terms for the entire contract period. | Licensing | 2025-06-12 | Legal & Procurement | Could require unplanned model substitution and integration effort. | Low | LLM covered by commercial licensing agreement. | Annual review of licensing terms and renewal clauses. | Open | 2025-10-01 | Vendor Contract
A031 | The LLM inference infrastructure (e.g., GPU/TPU availability) will support required performance at scale throughout project lifecycle. | Infrastructure | 2025-06-12 | Cloud Infrastructure Lead | Latency or availability issues affecting real-time analytics. | Medium | Provisioned with scalable cloud infrastructure and SLAs. | Performance monitoring and load testing. | Open | 2025-08-15 | Performance SLAs
A032 | Open-source components used in AI toolchain (e.g., transformers libraries) will remain actively maintained and secure. | Technical | 2025-06-12 | ML Engineering Lead | Increased security risk or need for forked maintenance. | Medium | Widely used OSS libraries with active contributors. | Track community activity and apply security patches. | Open | 2025-09-01 | Library Tracker
A033 | Updates to LLM safety filters or moderation mechanisms will not significantly alter system behavior without prior notice. | Model Governance | 2025-06-12 | AI Governance Lead | Unexpected refusal to process prompts or changed outputs. | Medium | Past vendor practice includes release notes and deprecation warnings. | Track vendor model release policies and changelogs. | Open | 2025-08-01 | AI Model Behavior Logs
A034 | There will be no significant changes to GDPR legislation that impact current data handling and processing practices for the duration of the project. | Regulatory | 2025-06-12 | Data Protection Officer | Could require changes to data pipelines, user consent flows, or storage policies. | Medium | Current GDPR framework has been stable in recent years. | Ongoing monitoring of EU/Nova Britannia legal updates. | Open | 2025-09-15 | Compliance Register
A035 | There will be no new restrictions or requirements imposed by national AI ethics guidelines that affect the AI system's decision-making processes. | AI Governance | 2025-06-12 | Ethics and Compliance Lead | System retraining or governance overhaul may be needed. | Medium | No immediate regulatory proposals under review. | Monitor national AI policy task force publications. | Open | 2025-09-01 | AI Decision Engine
A036 | Nova Britannia’s data protection authority will not introduce retroactive interpretations of compliance requirements. | Regulatory | 2025-06-12 | Legal Counsel | Might affect archived data or previously approved workflows. | Low | Stable precedent in regulatory approach. | Engage with regulatory updates via industry channels. | Open | 2025-12-01 | Data Governance Policy
A038 | The allocated room for the HPO will have sufficient power capacity and distribution to support high-performance computing and AV equipment. | Facilities / Power | 2025-06-12 | Facilities Lead | Risk of overloading circuits, requiring electrical redesign. | Medium | Standard requirements for digital command centers. | Site inspection and load analysis before fit-out. | Open | 2025-07-15 | Fit-Out Plan
A039 | Ambient lighting and glare control will be adequate or can be modified to suit holographic display requirements. | Facilities / Lighting | 2025-06-12 | UX Lead | Suboptimal user experience and reduced visual clarity. | Medium | Lighting critically affects holographic projection. | Lighting audit during initial site assessment. | Open | 2025-07-15 | Visual Design Guidelines
A040 | The room will support ergonomic configuration including adjustable workstations and collaborative space layout. | Facilities / Ergonomics | 2025-06-12 | Design Lead | Potential health and safety issues; poor productivity. | Low | Ergonomics required by workplace regulations. | Ergonomic design standards applied to layout plan. | Open | 2025-07-20 | Room Layout
A041 | AV and network cabling will be completed in advance of hardware installation. | Facilities / AV | 2025-06-12 | AV Engineer | Delays in system deployment and configuration. | Medium | Fit-out schedule must precede system delivery. | Confirm cabling with facilities team by Month 2. | Open | 2025-08-01 | Deployment Schedule
A042 | Room access, HVAC, and fire suppression systems will meet safety and operating requirements for sensitive digital equipment. | Facilities / Environment | 2025-06-12 | Health & Safety Lead | Equipment damage, overheating, or compliance failure. | Low | Modern office building expected to meet standards. | Site readiness inspection pre-deployment. | Open | 2025-07-25 | Pre-Go Live Checklist
A043 | The full design and fit-out of the HPO room will be completed within a 10-week timeframe prior to Month 7 deployment. | Scheduling | 2025-06-12 | Project Manager | May delay installation or require phased deployment. | Medium | Industry standard for medium-complexity fit-outs. | Track progress against agreed construction timeline. | Open | 2025-08-15 | Deployment Plan
A044 | The Buyer is responsible for the full design and physical fit-out of the HPO room, including readiness for hardware deployment. | Client Responsibility | 2025-06-12 | Commercial Lead | Delays or misalignment could affect delivery schedule and milestone payments. | Medium | Fit-out responsibilities not covered in Supplier scope. | Clarify responsibility in contract agreement. | Open | 2025-07-01 | Deployment Schedule
A045 | Any delays caused by the Buyer’s design or fit-out contractor will result in timeline impacts and additional costs, which will be passed to the Buyer. | Commercial / Risk Allocation | 2025-06-12 | Commercial Lead | Financial risk exposure and loss of margin for Supplier. | Medium | Contractual cost allocation to be confirmed. | Include cost impact clauses in contract terms. | Open | 2025-07-01 | Contract Clauses
A046 | Inflation will remain within the central bank's forecast range and will not materially affect project delivery costs. | Economic / Inflation | 2025-06-12 | Finance Director | Increased cost of goods and services could reduce project margins. | Medium | Based on Nova Britannia's latest inflation forecast. | Quarterly review of inflation indices. | Open | 2025-09-01 | Financial Risk Register
A047 | Interest rates will not significantly increase in a way that impacts project financing or operational borrowing costs. | Economic / Interest Rates | 2025-06-12 | Finance Director | Higher financing costs may require internal budget adjustments. | Medium | Interest rates projected to stabilize over short term. | Monitor central bank policy updates. | Open | 2025-10-01 | Financial Forecast
A048 | No new corporate taxes or levies will be introduced that affect profitability or delivery costs during the contract period. | Economic / Tax Policy | 2025-06-12 | Head of Tax | Unexpected tax changes may reduce profitability. | Low | Current tax policy environment is stable. | Engage with policy updates via tax advisory firm. | Open | 2025-12-01 | Financial Risk Register